HUGUENOT HUNDRED COMMUNITY ASSOCIATION

SPECIAL MEETING

APRIL 2, 2006 (4:00 P.M. at the River Area)

Purpose: to discuss a proposal to repair and replace the current dock/riverfront area.

Meeting format:  primarily a question and answer/discussion session with representatives of the Board and the River Area Maintenance Committee (chaired by Steve Thompson).  An opportunity to vote will be allowed at the end of the meeting.

Vote:  given the magnitude of the project in relationship to the Association’s finances, we will give three opportunities for members to vote:

- by proxy vote (included with this notice) in advance of the meeting

- by vote at the meeting

- for up to one week following the meeting

Background: the longevity and safety of our current dock has become questionable.  It appears that it is stable for the immediate future but it is highly doubtful that it will survive another three years (at the most).  Options include repairing on as an-needed basis; repairing on a systematic basis; complete replacement with commercial quality product; or not having a dock.  Upon obtaining a favorable quote for a complete replacement, a petition was made by 20% of the membership to hold a special meeting and vote to consider the dock project on an expedited basis.   Advantages of beginning work on an expedited basis include having the work completed in time for the beginning of summer and locking into a favorable quote.

Description of proposed repair and replacement project (schematic attached):

The project will begin with the demolition and removal of all existing wood on the dock and stairs.  Next will be the removal of about 7 tons of mud and silt from the sides of the boat ramp and under the old dock.  This will prepare the site for the new stairs, pier, and dock.  The wood along the upriver side of the boat ramp will not be removed but some of the mud from behind it will be removed to ease the pressure and improve appearance. 

The second phase will be the framing of the stairs, the new cement pad, and the building of the bulkhead with the pier on top of it.  The bulkhead will be 32 feet long and will be made of tongue and grove pressure treated wood.  This bulkhead will be angled downriver to create a small current to keep the silt from settling on our ramp as it does ever flood.  This “angling” of the bulkhead is a technique that helps but does not prevent silt build-up.  The pilings of the bulkhead will be driven into the ground by pounding.  Pilings will have an 8” butt and will from 12 to 14 feet long.

The last phase will be the pier surface of 32 feet long and 5 feet wide, which is much wider than the 3 feet we have today. The dock at the end will also have driven pilings and will be larger than the current dock measuring 14 foot along the river and eight foot deep.   The project also includes a new ladder that will consist of 2 x 4’s.

Other items that have been discussed and that would make good meeting topics include a floating dock, the decking meeting flush with the ramp, and a potential silt/mud cleaning pump system.

Terms:  approximately $10,000; to begin work approximately six weeks after receiving the order and deposit; approximately one week of work

Financial considerations:

The cost of this project would absorb approximately $10,000 of our $13,000 cash balances and would, therefore, seriously deplete any “rainy day” funds of the Association.   However, please bear in mind that regardless of your personal use, we all benefit from an improved river area through increased real estate values.

Financing options include:

- use the existing cash balances of the Association under the argument that this is a perfect use of the funds

- make a special assessment (one-time or spread over a term of years) to the entire membership to cover all or a portion of the cost

- increase “key” fees (one time or multiple) to recover a portion of the cost from the users most likely to use the new dock

- commit to the project at this time and wait until the annual May meeting to finalize the financing plan in conjunction with other proposals

====